## Sheet1
CAP 2 Task | Status (16 April 2014) | CAP 2 Due Date | NPS Position (16 April 2014) | NPS CAP 2 Final Status
Branch chief narrative survey plans | Archaeology received and accepted; Architecture survey plan submitted and not accepted; no other survey plans received or accepted | 2013-09-30 | partially achieved | accept archaeology and architecture products submitted achieved
IT strategic plan for archiving SHPD documents | not submitted | 2013-09-30 | not achieved | no IT strategic plan for archiving documents submitted not achieved
IT strategic plan for enhancing the intake database | not submitted | 2013-09-30 | not achieved | no IT strategic plan for the intake database submitted not achieved
Submission of documents explaining why FY13 taks outlined in the Statewide plan have not been accomplished | not submitted | 2013-09-30 | not achieved | submission not fully explanatory partially achieved
Submission of a SHPD office strategic plan and work plan | not submitted | 2013-09-30 | not achieved | submission not acceptable not achieved
Submission of employee work plans | Archaeology received and accepted; GIS received and accepted; Architecture received and not accepted; no other work plans received or accepted | 2013-09-30 | partially achieved | accept archaeology, architecture, GIS, National Register, CLG and tax credit submissions; no IT or administrative work plans submitted partially achieved
Submission of SHPD office procedures SOP | not submitted | 2013-09-30 | not achieved | no office procedures SOP submitted not achieved
Functional SHPD inventory GIS and database (architecture and archaeology, including burials) | several plans submitted and not accepted; no schemas produced or submitted; SHPD beta-testing archaeology database without consultation; SHPD refusing technical advice regarding SHPO databases | 2014-05-01 | not achieved | accept GIS data and metadata; no database submitted, plan submitted not acceptable partially achieved
CLG procedures and Hawaii CLG manual | submitted to NPS for review, currently being reviewed and expected to be accepted | 2014-05-01 | achieved | accept submission achieved
SHPD to hire Librarian or provide explanation of why not accomplished and provision of plans to accomplish tasks without the staff | no librarian hired, no plans submitted; SHPD submitted position description to HR although no progress made | 2014-05-01 | partially achieved | submission not fully explanatory partially achieved
SHPD to hire remaining professional staff to carry out Federal mandate or provide explanation of why not accomplished | hiring of necessary staff accomplished or in process | 2014-05-01 | partially achieved | submission not fully explanatory partially achieved
Submission of revised and updated Survey and Inventory SOP | Archaeology survey and inventory SOP in process but not submitted or accepted; Architecture survey and inventory SOP in process but not submitted or accepted; no other SOPs submitted or accepted | 2014-05-31 | partially achieved | accept archaeology and architecture survey and inventory SOPs submitted achieved
Submission of revised and updated Review and Compliance SOP | no review and compliance SOP submitted or in process | 2014-05-31 | not achieved | accept archaeology and architecture review and compliance SOPs submitted achieved
Submission of revised and updated National Register SOP | no National Register SOP submitted or in process | 2014-05-31 | not achieved | no revised or updated National Register SOP submitted not achieved
Submission of National Register public facing explanation of processes, benefits and progress | no public facing National Register information submitted or in process | 2014-05-31 | not achieved | accept submission achieved
CLG staff submits contracting and grant management SOP | no CLG contracting and grant management SOP submitted or in process | 2014-05-31 | not achieved | accept submission achieved
SHPD will conduct audit for period of CAP1 and CAP2 | audit being contracted but not completed or started | 2014-05-31 | partially achieved | no audit results or contract submitted not achieved
Submission of all PA's and MOA's for review | PA's and MOA's submitted | on-going | achieved | no information submitted, can not review
Submission of all required funding request documents | some documents have been submitted | on-going | partially achieved | no information submitted, can not review
GIS submits annual work plan for legacy data and new spatial data creation | submitted and accepted | on-going | achieved | accept submission achieved
GIS submits GIS program strategic plan | submitted and accepted | on-going | achieved | accept submission achieved
IT submits annual work plan for building the inventory database (architecture and archaeology) | not submitted or in process | on-going | not achieved | no IT annual work plan submitted not achieved
IT submits IT program strategic plan | not submitted or in process | on-going | not achieved | no IT strategic plan submitted not achieved
GIS and IT staff provide training to SHPD staff for maintenance and use of inventory GIS and database | GIS training conducted based on existing data; no database created so no training conducted | on-going | partially achieved | GIS training conducted; no inventory database created and no training conducted partially achieved
SHPD to make inventory accessible to agencies who have entered into a PA to access eligibility decisions | no database created, no PA's created | on-going | not achieved | no information submitted, can not review
Submission of plan to incorporate past eligibility decisions into the inventory database | no database created, no plans submitted or in process | on-going | not achieved | no plan to incorporate past eligibility decisions into inventory submitted not achieved
SHPD to develop website to track review and compliance project status | no website developed | on-going | not achieved | no process to track review and compliance project status for the public submitted not achieved
SHPD administration submits list of Sec 106 training taken for each employee and future plans for training | no Sec 106 training history or plans submitted | on-going | not achieved | accept submission achieved
SHPD to create internal digital National Register tracking log | no log submitted for review or in process | on-going | not achieved | no National Register tracking log submitted not achieved
SHPD will coordinate review of National Register nominations and SOPs with NPS | no SOPs submitted for review; nominations submitted under review | on-going | partially achieved | no National Register SOPs submitted; nominations submitted under review partially achieved
CLG staff to attend and complete CLG and grant management training | CLG staff completed training | on-going | achieved | accept submission achieved
CLG staff will provide scopes of work for proposed CLG projects for review | CLG project scopes of work submitted for review and accepted | on-going | achieved | accept submission achieved
CLG staff will provide draft products for subgrants awarded | CLG project draft products submitted for review and accepted | on-going | achieved | accept submission achieved
CLG staff will provide documentation of annual CLG reviews | no annual CLG review documentation submitted | on-going | not achieved | accept submission achieved
SHPD administration submits property inventory with source fund information | no property inventory submitted | on-going | not achieved | accept submission achieved
SHPD branch chiefs submit coordinated budget and strategic plans | no coordinated budget or strategic plans submitted | on-going | not achieved | no coordinated budget or strategic plan submitted not achieved